## as pivot table
Project | Activity | Resource | Unit Type | 01-JAN-2013 | 01-FEB-2013 | 01-MAR-2013 | 01-APR-2013 | 01-MAY-2013 | 01-JUN-2013 | 01-JUL-2013 | 01-AUG-2013 | 01-SEP-2013 | 01-OCT-2013 | 01-NOV-2013 | 01-DEC-2013
CostDemo1 | CD1-1000 | COST 1 - DESIGN | Remaining |  | 2000
CostDemo1 | CD1-1000 | COST 1 - DESIGN | Planned |  |  | 8000
CostDemo1 | CD1-1000 | COST 2 - ON BUILD | Planned |  |  |  |  | 15000 | 20000 | 25000
CostDemo1 | CD1-1000 | COST 3 - MISC | Planned |  | 1000 |  | 3000
CostDemo1 | CD1-2000 | COST 1 - DESIGN | Planned |  |  |  |  | 1000 | 5000 | 6000 | 7000
CostDemo1 | CD1-2000 | COST 2 - ON BUILD | Planned | [9 empty] | 9000 | 10000 | 12000
CostDemo1 | CD1-2000 | COST 3 - MISC | Planned |  |  |  |  | 500 | 600 | 700
CostDemo2 | CD2-6000 | COST 1 - DESIGN | Planned |  |  |  | 100 | 200
CostDemo2 | CD2-6000 | COST 2 - BUILD | Planned | [6 empty] | 15000
CostDemo2 | CD2-6000 | COST 3 - MISC | Planned | [5 empty] | 500
CostDemo2 | CD2-7000 | COST 1 - DESIGN | Remaining | 900 | 700
CostDemo2 | CD2-7000 | COST 2 - BUILD | Remaining |  |  |  | 1300 | 1700
CostDemo2 | CD2-7000 | COST 3 - MISC | Remaining |  | 200

## Sheet1
Project | Activity | Resource | Unit Type | Units | Period Date
CostDemo1 | CD1-1000 | COST 1 - DESIGN | Remaining | 2400 | 2013-02-01
CostDemo1 | CD1-1000 | COST 1 - DESIGN | Planned | 9600 | 2013-03-01
CostDemo1 | CD1-1000 | COST 2 - BUILD | Planned | 18000 | 2013-05-01
CostDemo1 | CD1-1000 | COST 2 - BUILD | Planned | 24000 | 2013-06-01
CostDemo1 | CD1-1000 | COST 2 - BUILD | Planned | 30000 | 2013-07-01
CostDemo1 | CD1-1000 | COST 3 - MISC | Planned | 1200 | 2013-02-01
CostDemo1 | CD1-1000 | COST 3 - MISC | Planned | 3600 | 2013-04-01
CostDemo1 | CD1-1000 | COST 3 - MISC | Actual | 600 | 2013-02-01
CostDemo1 | CD1-2000 | COST 1 - DESIGN | Planned | 1200 | 2013-05-01
CostDemo1 | CD1-2000 | COST 1 - DESIGN | Planned | 6000 | 2013-06-01
CostDemo1 | CD1-2000 | COST 1 - DESIGN | Planned | 7200 | 2013-07-01
CostDemo1 | CD1-2000 | COST 1 - DESIGN | Planned | 8400 | 2013-08-01
CostDemo1 | CD1-2000 | COST 2 - BUILD | Planned | 10800 | 2013-10-01
CostDemo1 | CD1-2000 | COST 2 - BUILD | Planned | 12000 | 2013-11-01
CostDemo1 | CD1-2000 | COST 2 - BUILD | Planned | 14400 | 2013-12-01
CostDemo1 | CD1-2000 | COST 3 - MISC | Planned | 600 | 2013-05-01
CostDemo1 | CD1-2000 | COST 3 - MISC | Planned | 720 | 2013-06-01
CostDemo1 | CD1-2000 | COST 3 - MISC | Planned | 840 | 2013-07-01
CostDemo1 | CD1-2000 | COST 3 - MISC | Actual | 9600 | 2013-10-01
CostDemo2 | CD2-6000 | COST 1 - DESIGN | Planned | 120 | 2013-04-01
CostDemo2 | CD2-6000 | COST 1 - DESIGN | Planned | 240 | 2013-05-01
CostDemo2 | CD2-6000 | COST 1 - DESIGN | Actual | 1800 | 2013-07-01
CostDemo2 | CD2-6000 | COST 2 - BUILD | Planned | 18000 | 2013-07-01
CostDemo2 | CD2-6000 | COST 3 - MISC | Planned | 600 | 2013-06-01
CostDemo2 | CD2-7000 | COST 1 - DESIGN | Remaining | 1080 | 2013-01-01
CostDemo2 | CD2-7000 | COST 1 - DESIGN | Remaining | 840 | 2013-02-01
CostDemo2 | CD2-7000 | COST 2 - BUILD | Remaining | 1560 | 2013-04-01
CostDemo2 | CD2-7000 | COST 2 - BUILD | Remaining | 2040 | 2013-05-01
CostDemo2 | CD2-7000 | COST 2 - BUILD | Actual | 1140 | 2013-04-01
CostDemo2 | CD2-7000 | COST 3 - MISC | Planned | 240 | 2013-02-01

## activity data
Project | Activity | Name | Start | Type
CostDemo1 | CD1-1000 | cost demo | 2013-01-01 | fixed duration and units
CostDemo1 | CD1-2000 | cost demo | 2013-01-02 | fixed duration and units
CostDemo2 | CD2-6000 | cost demo | 2013-01-03 | fixed duration and units
CostDemo2 | CD2-7000 | cost demo | 2013-01-04 | fixed duration and units